## Sheet1
Risk Matrix for SkateXut Project
Risk# | Risk Description | Statement | Response | Impact | Likelihood | Severity
1 | Procrasination /focus | I’m prone to procrasinating or lack of focus, which with the small time frame would be critical | Deleted social media, Focus on the project as much as possible, treat myself for hard work, go outside for short walks, talk with coursemates | 25 | Very Likely | Severe
2 | Stress | It’s been a tough few weeks, so there is a lot on my mind and hard to get over defeats | Persist at the challenge and remind myself I’m great | 15 | Likely | Moderate
3 | Databases not working | Because I’m new to H2 I’m guarenteed to run into problems which would significantly affect the overall project and time spent | Ask for help and research | 20 | Likely | Severe
4 | Git merge conflicts | Merge conflicts can be a real pain | Keep consistent merges where possible | 20 | minor | Significant
5 | Research Rabbit holes | When running into a problem it can be easy to run into rabbit holes when trying to fix one problem, leading to more problems | Ask for help and research effecitvely, dissect the problem and read errors | 14 | Likely | Moderate
6 | Time limit | We have a limited time to complete the entire project | Be persistent, and don’t fall into usual habits. Let the ADHD in me that can focus and enjoy work that brings me joy | 15 | Very Likely | Significant
7 | New to Java | I’m new to java and spring boot, and it’s quite an experience, even with my existing knowledge | Use all the recourses at my disoposle, and try not to over complicate | 12 | Likely | Moderate
8 | Testing | Testing can always be a pain, and problematic | Get out ahead as quickly as possible to try and resolve any potential issues in a times manor | 10 | Likely | minor
Negligible | Minor | Moderate | Significant | Severe | Severity
5 | 10 | 15 | 20 | 25 | Impact
4 | 9 | 14 | 19 | 24
3 | 8 | 13 | 18 | 23
2 | 7 | 12 | 17 | 22
1 | 6 | 11 | 16 | 21
likelihood | Very Likely
Likely
Possible
Unlikely
Very Unlikely